## create an excel sheet with the
Sprint | Task ID | Task | Task Description | Assignee | Priority | Estimated MD | Remaining MD | Status | Notes
1 | 1 | environment setup | installing nrf coneect extension pack in vs code and nrf connect sdk desktop |  | high | half day | 0 | done
| 2 | sample code running | to blink the the led in nrf52840 |  | low | 1 hour | 0 | done
| 3 | WS2812B Driver Implementation | Implementing the timing-sensitive NeoPixel protocol using PWM with EasyDMA to ensure non-blocking operation. |  | high | 2 day |  | to do
| 4 | IR Sensor Integration | Wiring the IR obstacle sensor and writing a debouncing/gating algorithm to prevent false triggers during high-speed movement. |  | high | 2 day |  | to do
2 | 5 | sample code running | bluetooth simple serial profiles |  | low | 2 days |  | to do
| 6 | BLE Master-Peripheral Architecture Setup | Establishing a stable Star Network; configuring the nRF52840 as Master to scan and connect to Pods 1-4. |  | medium | 2 days |  | to do
| 7 | Custom BLE Service/Characteristic Design | Designing a protocol to send "Trigger" commands (LED color) and receive "Hit" notifications (Sensor data) with low latency.1 |  | medium | 2 days |  | to do
| 8 | Zephyr Thread & Priority Mapping | Defining thread priorities to ensure time-critical tasks (BLE and IR Sensor) preempt lower-priority tasks (LED animations). |  | medium | 2 days |  | to do
| 9 | Inter-Thread Communication (IPC) | Setting up Message Queues to safely pass "Hit" data from the Sensor thread to the BLE thread without data corruption. |  | medium | 2 days |  | to do
3 | 8 | Game Mode 1: Reaction Time | Developing the logic for random Pod activation and measuring the time delta between LED "On" and IR "Hit." |  | medium | 2 days |  | to do
| 8 | Game Mode 2: Cognitive Training | mplementing color-coded logic (e.g., hit Green, avoid Red) to test decision-making under pressure. |  | medium | 2 days |  | to do
| 10 | Game Mode 3: Memory Sequence | Developing a "Simon Says" style sequence where the user must hit pods in a specific recorded order. |  | medium | 2 days |  | to do
4 | 11 | casing making | making 4 pod casings |  | medium | 4 days |  | to do
| 12 | Hardware Enclosure & Cable Management | Mounting the circular LED board and IR sensor into the pod housing. |  | medium | 2 days |  | to do
| 13 | Latency Optimization & Debugging | Stress testing the BLE connection under load and tuning the IR sensor sensitivity for different lighting conditions. |  | medium | 2 days |  | to do
Abbreviations
| PS | Platform Setup
| DRV | Driver and RTOS integration
| APP | Application
| QA | Quality Assurance